## TestCase
|  |  | Test Case Developed by |  | Ibrahim khalil | [5 empty] | TEST CASE
Product Name | XYZ for Web |  | TC Start date |  | 16-12-2022 | [5 empty] | PASS | 46
Module Name | Test Cases for Registration |  | TC End date |  | 18-12-2022 | [5 empty] | FAIL | 5
EPIC |  |  | Test Case Reviewed By |  | Sabul Islam,IT Training BD | [5 empty] | Not Executed | 30
[11 empty] | Out of Scope | 0
[11 empty] | TOTAL | 81
#SL | Module | Type of Testing | Features | Test Cases Description | Test Data | Test Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC-001 | Test Cases for Registration | Functional Testing | Verify all valid information with registration forms | Correct information with proper name, email,address,phone number | Name: Ibrahim khalil Email:ibrahimcse.green@gmail.com Password: Green@12 Repassword: Green@12 | 1.Go to link | Susscessfully Create account | Susscessfully Create account | Valid form Reg |  | Passed
2.Click on the uper right corner sildebar signup button
3.Then go to the registration page
4.Fill up the all valid information
5.Click Registration Button
TC-002 |  |  | Verify blank data with registration forms | Check blank data information | No data value | 1.Go to link | A warning message shall be shown addressing."Please fill out this field" | Showed warning message."Please fill out this field" | Empty form input |  | Not Executed
2.Click on the uper right corner sildebar signup button
3.Then go to the registration page
TC-008
TC-009 | [10 empty] | Passed
TC-010 | [10 empty] | Passed
TC-011 | [10 empty] | Passed
TC-012 | [10 empty] | Passed
TC-013 | [10 empty] | Passed
TC-014 | [7 empty] | Allow special character. |  |  | Failed
TC-015 | [10 empty] | Not Executed
TC-016 | [10 empty] | Not Executed
TC-017 | [7 empty] | Did not allow negative number . |  |  | Passed
TC-018 | [7 empty] | Showed warning message. |  |  | Passed
TC-019 | [10 empty] | Not Executed
TC-020 | [10 empty] | Not Executed
19 | [10 empty] | Not Executed
20 | [7 empty] | Showed warning message. |  |  | Passed
21 | [10 empty] | Not Executed
22 | [10 empty] | Not Executed
23 | [10 empty] | Not Executed
24 | [10 empty] | Not Executed
25 | [10 empty] | Not Executed
26 | [10 empty] | Not Executed
27 | [10 empty] | Not Executed
28 | [10 empty] | Not Executed
29 | [10 empty] | Not Executed
30 | [7 empty] | Showed message. |  |  | Passed
31 | [7 empty] | It was working properly. |  |  | Passed
32 | [7 empty] | Showed Purchase Option. |  |  | Passed
33 | [7 empty] | Not Correct |  |  | Failed
34 | [7 empty] | Yes. |  |  | Passed
35 | [7 empty] | Not Correct |  |  | Failed
36 | [7 empty] | Not Blank |  |  | Passed
37 | [7 empty] | showed a valid format. |  |  | Passed
38 | [10 empty] | Not Executed
39 | [7 empty] | Yes. |  |  | Failed
40 | [7 empty] | Yes. |  |  | Passed
41 | [10 empty] | Not Executed
Passed
42 | [7 empty] | Showed warning message. |  |  | Passed
43 | [7 empty] | Yes. It was in correct format. |  |  | Passed
44 | [7 empty] | Yes. It was in correct format. |  |  | Passed
45 | [10 empty] | Passed
46 | [7 empty] | Yes. It was in correct format. |  |  | Passed
47 | [7 empty] | Not in BDT. |  |  | Failed
48 | [7 empty] | Yes. It was in correct format. |  |  | Passed
49 | [7 empty] | Did not allow negative input values |  |  | Passed
50 | [10 empty] | Not Executed
51 | [7 empty] | Allowed Blank input. |  |  | Passed
52 | [7 empty] | Did not allow the negative. |  |  | Passed
53 | [7 empty] | Yes. It can be blank. |  |  | Passed
54 | [7 empty] | yes. Mathced with the exact brands. |  |  | Passed
55 | [7 empty] | Yes. It does not allow Negative Integer. |  |  | Passed
56 | [10 empty] | Not Executed
57 | [10 empty] | Not Executed
58
59 | [7 empty] | Yes. It was active |  |  | Passed
60 | [7 empty] | Yes.It allowed only positive integer. |  |  | Passed
61 | [7 empty] | Yes. It allowed both character and positive integer. |  |  | Passed
62 | [10 empty] | Not Executed
63
64
65 | [7 empty] | Yes . It is working properly. |  |  | Passed
66 | [10 empty] | Not Executed
67 | [7 empty] | Yes. It added row with click. |  |  | Passed
68 | [7 empty] | Yes. It was working. |  |  | Passed
69 | [7 empty] | Yes. It was working properly. |  |  | Passed
70 | [7 empty] | It was ok. |  |  | Passed
71 | [7 empty] | Yes. It was in correct format. |  |  | Passed
72 | [7 empty] | Yes. It was working properly. |  |  | Passed
73 | [7 empty] | It allowed blank input. |  |  | Passed
74 | [7 empty] | It allowed blank input values. |  |  | Passed
75 | [7 empty] | It allowed decimal and positive integer. |  |  | Passed
76 | [7 empty] | It allowed decimal and positive integer. |  |  | Passed
77 | [7 empty] | It allowed decimal input. |  |  | Passed
78 | [7 empty] | It gave response with mouse click. |  |  | Passed
79 | [10 empty] | Not Executed
80 | [10 empty] | Not Executed
81 | [10 empty] | Not Executed
82 | [10 empty] | Not Executed
83 | [10 empty] | Not Executed
84 | [10 empty] | Not Executed
85 | [10 empty] | Not Executed
86 | [10 empty] | Not Executed
87 | [7 empty] | Yes. It was working. |  |  | Passed
88
89
90
Negative test

## Report
Test Case Report
Project Name - | barikoi.com
Module Name - | Test Case Registration |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 8 | PASS
Written By | Ibrahim khalil |  |  |  |  | 6 | FAIL
Executed By | Ibrahim khalil |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 2 | Warning |  |  | Test Environment | Microsoft Dev Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 46 | 5 | 30 | 0 | 81
Grand Total | 46 | 5 | 30 | 0 | 81
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## barikoi.com Test Case
[5 empty] | Test Case Developed By | Ibrahim khalil |  | TEST CASE
| Product Name |  | barikoi.com |  | TC Start Date | 16-12-2022 |  | PASS | 8
| Module Name |  | Test Cases for Registration |  | TC End Date | 18-12-2022 |  | FAIL | 6
| EPIC |  |  |  | Browser (tested) | 1 |  | WARNING | 2
| Test Case Reviewed By |  | Samiha Jahan |  | Performance (tested) | No |  | Not Execute
[8 empty] | TOTAL | 16
#SL | Module | Type of Testing | Feature | Test Case Description | Test Data | Step Description | Expected data |  | Actual Data | Bug Screenshots | Enviroment | Dev Comments | Status
TC_001 | Test Cases for Registration | Fuctional Testing | Verify all valid information with registration forms | Correct information with proper name, email address,phone number and password | Name: Ibrahim khalil Number:01954504900 Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to Microsoft Dev Browser | Successfully Create account |  | Sucessessfully Create Account |  | Operating system: Windows 10, windows 11 Software: Microsoft Dev, Chorme Search engine: Bing,Google |  | Passed
2.Go to barikoi.com
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Fill up the all valid information
5.Click Registration Button
TC_002 |  |  | Verify if the user cannot proceed without filling all mandatory fields. | Empty Data with mandatary fields | None | 1.Go to Microsoft Dev Browser | A warning message shall be shown addressing."Please fill out this field" |  | Showed warning message."Please fill out this field" |  |  |  | Passed
2.Go to barikoi.com
3.Click on the uper right corner sildebar Account->signup button
4.Then go to the registration page
5.Blank data
6.Click Registration Button
TC_003 |  |  | Verify if the numbers is not allowed in the name field | Name fields input with only number | Name: 4312 | 1.Go to Microsoft Dev Browser | Successfully Create account |  | Allow Number | Input number name field |  |  | Failed
2.Go to barikoi.com
3.Click on the uper right corner sildebar Account->signup button
4.Then go to the registration page
5.name field number
6.Click SIGNUP Button
TC_004 |  |  | Verify if the Numbers and Special characters are not allowed in the name field | Name fields input with Special character and character | Name:ibr$him | 1.Go to Microsoft Dev Browser | Successfully Create account |  | Allow Special character | Input Special Character | Operating system: Windows 10, windows 11 Software: Microsoft Dev, Chorme Search engine: Bing,Google |  | Failed
2.Go to barikoi.com
3.Click on the uper right corner sildebar Account->signup button
4.Then go to the registration page
5.name field Special charater
6.Click SIGNUP Button
TC_005 |  |  | Verify if the very short name is not allowed in the name field | Checking name fields input with Short name character | Name:ibr | 1.Refresh the page | Successfully Create account |  | Allow Short Name |  |  |  | warning
2.short name input with all field fillup
5.Click SIGNUP Button
TC_006 |  |  | Verify if the long character is not allowed in the name field | Checking name fields input Long character | Name:ibrahimhalilifty | 1.Go to barikoi.com | Successfully Create account |  | Allow Long name | Input Long Character |  |  | warning
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.name field long charater
5.Click SIGNUP Button
TC_007 |  |  | Verify if the emails address will not get assigned | valid email address should be assigned | Email:ibrahimcse.green@gmail.com | 1.Go to barikoi.com | Successfully Create account |  | It's correct go to the next page |  |  |  | Passed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Valid email address
5.Click SIGNUP Button
TC_008 |  |  | Varify Invalid email address check | Try email fields input invalid email address | Email:ibrahimcse.green#gmail.com | 1.Go to barikoi.com | A warning message shall be shown addressing." Please including '@' in the email" |  | Showed warning message."Please including '@' in the email" | Waring Showed | Operating system: Windows 10, windows 11 Software: Microsoft Dev, Chorme Search engine: Bing,Google |  | Passed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Invalid email address
5.Click SIGNUP Button
TC_009 |  |  | Varify Invalided domain email address check | Entering the email fields invalid domain email address | Email:ibrahimcse.green@xyz.com | 1.Go to barikoi.com | Successfully Create account |  | It's not correct but go to the next page | Invaild domain email |  |  | Failed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Invalid domain email address
5.Click SIGNUP Button
TC_010 |  |  | Varify Invalided phone number | Checking phone number fields input with invalid phone number | Name: Ibrahim khalil Number:011222002212 (12) Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com | Successfully Create account |  | It's not correct but go to the next page | Invaild phone number |  |  | Failed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.12 digit phone number
5.Click SIGNUP Button
TC_011 |  |  | Varify if the mobile number field with Letter | Entering the Mobile number with Letter | Name: Ibrahim khalil Number:011222002x2 Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com | A warning message shall be shown addressing."The phone number must be number.we are expecting 11 to 15 digit" |  |  | Letter with phone number |  |  | Passed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Input x Letter with phone number
5.Click SIGNUP Button
TC_012 |  |  | Varify number with special character input value | Mobile number with Special charater | Name: Ibrahim khalil Number:019222002$2 Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com | A warning message shall be shown addressing."The phone number must be number.we are expecting 11 to 15 digit" |  | It's not correct but go to the next page | Special Charater with phone number | Operating system: Windows 10, windows 11 Software: Microsoft Dev, Chorme Search engine: Bing,Google |  | Passed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.input 12 digit phone number
5.Click SIGNUP Button
TC_013 |  |  | Verify if duplicate mobile number will not get assigned | Exiting mobile number | Name: Ibrahim khalil Number:01954504900 Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com |  |  | It's not correct but go to the next page | Invaild phone number |  |  | Failed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.Input phone number
5.Click SIGNUP Button
TC_014 |  |  | Verify if duplicate email addresh will not get assigned | Exiting email Account | Name: Ibrahim khalil Number:01954504900 Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com |  |  | It's not correct but go to the next page |  |  |  | Passed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.12 digit phone number
5.Click SIGNUP Button
TC_015 |  |  | Verify if the password field will promote for wea paswords | short password | Name: Ibrahim khalil Number:01922200221 Email:ibrahimcse.greepn@gmail.com Password: 1235678 | 1.Go to barikoi.com |  |  | It's not correct but go to the next page |  |  |  | Failed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.12 digit phone number
5.Click SIGNUP Button
TC_016 |  |  | invalid passwod | Invalided domain email address | Name: Ibrahim khalil Number:011222002212 (12) Email:ibrahimcse.green@gmail.com Password: Green@12 | 1.Go to barikoi.com |  |  | It's not correct but go to the next page |  |  |  | Failed
2.Click on the uper right corner sildebar Account->signup button
3.Then go to the registration page
4.12 digit phone number
5.Click SIGNUP Button
|  | Compactability Testing | Signin | Microsoft Dev | Should be able to

## Reported
R
Test Case Report
| Project Name - | barikoi.com
| Module Name - | Test Case Registration
| Test Case Version | -
| Written By | Ibrahim khalil
| Executed By | Ibrahim khalil
| Reviewed By | -
TEST EXECUTION REPORT
| Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
|  | 0 | 0 | 0 | 0 | 0 | Total No. | Status | Result :
| Grand Total | 0 | 0 | 0 | 0 | 0 | 8 | PASS
[7 empty] | 6 | FAIL
| LIMITATIONS | [5 empty] | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
| Documents |  |  |  | Received | Useful | 2 | Warning |  | Test Environment | Microsoft Dev Browser
| PRD |  |  |  | No | No
| USER STORY |  |  |  | No | No
|  | Testing Type in Scope | Description
| Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
| Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
| Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
| Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
| Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
| Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
| Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.